## Slide 1: CONOP 2025 Staff Ride Big Hole Battlefield
3 May 2025

## Slide 2: Commander’s Intent
Expanded Purpose: Grizzly Battalion completes staff-ride at Big Hole Battlefield in order to achieve understanding of social and political events that led to the conflict between the Nez Perce and the U.S. Army.
Key Tasks:
All MSIII/ MSIV participate in staff ride
Conduct a battle analysis of a specific leader in the battle
Meet the USACC intent for commissioning requirements
Endstates
Cadets: develop understanding of the U.S. Army and Nez Perce perspectives Complete assigned vignette readings and brief respective portion during staff ride in order to complete commissioning requirement.

## Slide 3
Packing List
Worn:
Civilians- collared shirt.
Light base layer
Wet weather top
Assault Pack:
2x MRE
3L Water
TIMELINE |  | 
Time | Event | Location
01MAR25 | Vignette assignments | Schriber
03APR25 | Site Recon- roster TBD | Wisdom, MT
01MAR25 | Final OPORD | Schriber
02 MAY25 |  | 
1300 | Cadet Vignette rehearsal | Schriber/teams
1430 | NLT final weather call | Helena
03MAY25 |  | 
0700 | Schools depart for L/U | UM/CC
0800 | L/U Garrison turnoff | 12T US 6204 5400
0945 | Arrive BHNB site | 12T TR 9401 5751
1000 | Park Ranger Briefing | Visitor Center
1115 | Begin Battlefield walk | Lower parking lot
1515 | Battlefield walk complete | Trails
1530 | AAR, gifts for BHNB staff, RTB | 
1830 | Both Schools RTB, | Missoula, Helena
Command and Signal:
Command:
  CO:
  1SG:
Signal:
P: Phone
A: ICOM channel 4
C: Time hack/runner
Training Management (8-STEP Training Model) |  |  |  |  |  |  | 
Plan the Training | Train Leaders | Recon the Site | Issue the Plan | Rehearse Training | Execute Training | Evaluate Training | Retrain
30DEC24 | 01MAR254 | 03APR25 | 21MAR25 | 02MAY25 | 03MAY25 | 03MAY25 | Various
3 May Staff Ride
Situation: AO: Big Hole battlefield, IVO Wisdom, MT Weather: H 60 L 35 Overcast 50% chance of rain
Mission: Grizzly BN conducts Staff Ride IOT establish historical perspective of military conflict in the western US. Commander’s Intent: The Purpose of this operation is to satisfy CCMD graduation requirements and build local understanding of military conflict in Montana in the late 1800’s End State: F: Cadets complete staff ride requirement for commissioning E: No Change T: Big Hole battlefield site remains intact for future operations C: Develop appreciation for military role in society
Concept of Operations: Phase 1: Planning/Preparation: Key Tasks: CONOP Creation, Recon, vignette preparation, air request and HLZ identification/authorization Phase 2: Execution: Key Tasks:. Coordinated MVT to/from objective, park ranger briefing, battlefield review and cadet vignettes Phase 3: Recovery/Assessment: Key Tasks: AAR, documentation of completion, cadet vignettes submitted for repository,
Manning |  | 
Role | Name | Responsibility
Cadre |  | 15 Pax Driver CC
Cadre |  | 15 Pax Driver UM
Cadre |  | 15 Pax Driver UM
Cadre |  | Graphics production, 2x 3’x4’ posters, 30 handouts
Cadre |  | Reading assignments, historical figure selection
Cadre |  | briefing formats, graphics identification
Cadets |  | Teams 1-6
Classes of Supply
CL I: MREs, Water
CL IV: N/A
CL V: None
CL VII: 3x vans
CL VIII: 1x CLS bag per school
Notes: Units can adjust the sizes of certain boxes if information does not fit.
Units can also change classes of supply they may require for event, for example not every event will include CL IV or CL V, but may include CL VIII

## Slide 4: Saturday, 03 MAY 25 GSA Scheme of Maneuver
OBJ
N
Lost Trail Pass Elev:7090’
UM Alternate 110 mi 2hr, 10 min
CC Primary 138 mi 2hr, 22 min
UM Primary 164 mi 3hr 10 min

## Slide 5: Actions on Objective
HELO Supported Timeline |  | 
Time | Event | Location
0845 | Notify BHB staff of ETA | 
0945 | Wheels down HLZ Big Hole | 1
1000 | Park Ranger Briefing | 2
1115 | Battlefield walk | 3
1230 | Wheels up HLZ Big Hole | 1
1
2
3
N
GSA Trans Timeline |  | 
Time | Event | Location
0700 | Both Schools SP for BHNB | 
0945 | Linkup at BHNB | 1b
1000 | Park Ranger Briefing | 2
1115 | Battlefield walk | 3
1200 | Bag Lunch at Seige area | 4
1b
4

## Slide 6: CASEVAC: Salmon, ID, 1 Hr 9 min
Primary ER location:
Steele Memorial Medical Center,
203 N Daisy St,
Salmon, ID 83467
208-756-5600
63 Road miles
34 air miles
Alt ER location
Barrett Hospital
600 state Hwy 91 S.
Dillon, MT 59725
406-683-3000
74 Road Miles
56 Air miles
Driver: CPT Beaty – 406-208-5413
CLS: SFC Harriman (68W) – 406-212-9787
VIC: GSA Van
Route Recon: Complete
N
On site CLS evaluates injured casualty and determines treatment plan
If additional MEDEVAC is necessary: Call 911
If Lost Trail Pass is restricted due to weather, CASEVAC to Dillon, MT.
If non-life threatening: utilize GSA van to transport to appropriate location
OBJ

## Slide 7: Alt CASEVAC: Dillon, MT, 1 Hr 14 min
Primary ER location:
Steele Memorial Medical Center,
203 N Daisy St,
Salmon, ID 83467
208-756-5600
63 Road miles
34 air miles
Alt ER location
Barrett Hospital
600 state Hwy 91 S.
Dillon, MT 59725
406-683-3000
74 Road Miles
56 Air miles
Driver: CPT Beaty – 406-208-5413
CLS: SFC Harriman (68W) – 406-212-9787
VIC: GSA Van
Route Recon: Complete
N
On site CLS evaluates injured casualty and determines treatment plan
If additional MEDEVAC is necessary: Call 911,
If non-life threatening: utilize GSA van to transport to appropriate location
OBJ
N

## Slide 8: MEDEVAC: +/- 40 minutes
Primary Trauma Care location:
Bozeman Health
915 Highland Blvd
Bozeman, MT 59715
(406)-414-5000
Alt ER location
Barrett Hospital
600 state Hwy 91 S.
Dillon, MT 59725
406-683-3000
74 Road Miles
56 Air miles
CLS: SFC Harriman (68W) – 406-212-9787
N
If additional MEDEVAC is necessary: Call 911,
Life flight response 30 minutes from Butte, 40 minutes from Missoula. Hospitals must coordinate life flight for authorization. 911 dispatch in charge of all coordination.
1x Dedicated Cadre (non-CLS) stays on phone with 911 until MEDEVAC arrives, then rides with Casualty to ER
If casualty is designated Urgent, or Urgent Surgical, request evacuation to Bozeman Health ACS Level 3
OBJ
Missoula
Butte
Bozeman
N

## Slide 9: MEDEVAC landing sites
Hwy 43
Power lines, 25’ AGL
Property Boundary
0
.1
.25
Distance (miles)
TIMELINE | 
Event | Location
Coordinate for Air MEDEVAC | 911
Notify BHNB staff of MEDEVAC | (406) 689-3155
Primary HLZ | 12T TR 9357 5733
Alt HLZ | 12T TR 9373 5747
PRI HLZ
ALT HLZ

## Slide 10: Vehicle Recovery Plan
Primary Tow Asset
Iron Horse Towing, INC
6593 U.S. Hwy 10W
Missoula, MT 59808
Personnel in the Field:
Call GSA Services phone number on back of GSA CC in dispatch folder to initiate tow vehicle movement. Report vehicle location in reference to town and closest mile marker.
Re-route 1x GSA from other school for cross-loading personnel.
Move vehicle sufficiently off road, turn on hazard lights, 2x Cadre standby for tow asset linkup.
If leaving vehicle, put keys in gas tank flap. Leave phone number for state patrol to call if they come mark the vehicle.
GSA Services:
GSA services will coordinate all tow vehicle and tire replacement.
Bozeman

## Slide 11: Deliberate Risk Assessment
Deliberate Risk Assessment Worksheet upon approval

## Slide 12: Risk Control Measures
Overall Risk Level: Low
Personnel Risks:
Cold Weather Injury- packing list, PCC’s
Group separation- brief terrain and map. Brief collection point and actions to take if separated from group.
Operational Risks:
CASEVAC- evacuation related to life, limb, eyesight will require a judgement call, realistic time to get casualty to a care facility via ground trans is comparable to civilian MEDEVAC response time unless utilizing MTARNG rotary assets for CASEVAC.
Weather-
relying on HELO as primary trans and CASEVAC limits options in inclement weather.
Lost Trail Pass road conditions may be substantially different than majority of routes
Environmental Risks:
Wildlife: Mitigated by Cadre/MS 4s carry bear spray
Slips trips and falls: keep group on improved paths, proceed through battlefield at moderate pace. Ensure proper foot ware during PCC’s